## Product Backlog
Project Name: World War Egg |  | GAM125 - Product Backlog
Team: W-W-E
Degree | Team Member (Full Name) | Team Role / Interests | Epics (Big Features)
Game Art & Animation and Advertising Art | Tiffany Roberts | Leader/Producer | Defines Core Funtionality, Fun Factor, & Innovation
Game Art & Animation (BFA) | Isabel Ramos | Artist | Epic 1: | Game Layout
Game Programming | Anthony Medina | Design | Epic 2: | Gameplay
Game Design | Jasmyn Svetic | Artist | Epic 3: | Storyline
Computer Science & Game Design | Kaitlyn Moeller | Design | Epic 4: | Aesthetic
Epic 5:
ID # | Part of Epic # | User Stories (Features) | Priority # | Estimated Sprint # | Date Added | Est. Time (Hours) | Total Hours: | 280
1 | Game Layout
2 |  | Determine tile status: normal, combat, trap, and cards | 1 | 1 | 2022-04-04 | 12
3 |  | Placement of tiles, players, and egg | 1 | 1 | 2022-04-04 | 12
4 | Gameplay
5 |  | Card Mechanics (3 decks? 15 cards?) | 1 | 1 | 2022-04-04 | 20
6 |  | Board Game Mechanics | 1 | 1 | 2022-04-04 | 20
7 |  | Player Movement (Dice) | 1 | 1 | 2022-04-04 | 4
8 |  | Combat | 1 | 1 | 2022-04-04 | 20
9 |  | Rule Book | 1 | 1 | 2022-04-04 | 20
10 | Storyline
11 |  | Why are they trying to get the egg? Why will the egg end the war? | 2 | 1 | 2022-04-04 | 6
12 |  | Where are they? | 4 | 1 | 2022-04-04 | 6
13 |  | Who are they? | 3 | 1 | 2022-04-04 | 6
14 |  | What is the goal? | 2 | 1 | 2022-04-04 | 6
15 |  | When is this taking place? | 3 | 1 | 2022-04-04 | 6
16 |  | How will the players get the egg? | 4 | 1 | 2022-04-04 | 6
17 | Aesthetics
18 |  | Original Ideas | 3 | 2 | 2022-04-04 | 10
19 |  | Card Art | 1 | 2 | 2022-04-04 | 30
20 |  | Cover of the game (box) ? | 5 | 2 | 2022-04-04 | 16
21 |  | Game Pieces | 2 | 2 | 2022-04-04 | 30
22 |  | Board Enviornment | 1 | 2 | 2022-04-04 | 50
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84
85
86
87
88
89
90
91
92
93
94
95
96
97
98
99
100