## Product Backlog
Project Name: World War Egg |  | GAM125 - Sprint Backlog
Team: W-W-E
Degree | Team Member (Full Name) | Team Role / Interests | Sprint Information
Game Art & Animation and Advertising Art | Tiffany Roberts | Leader/Producer | Sprint Number: | 1
Computer Science and Game Design | Kaitlyn Moeller | Designer
Game Art & Animation (BFA) | Isabel Ramos | Artist | Days In Sprint: | 14
Game Programming | Anthony Medina | Designer
Game Design | Jasmyn Svetic | Artist | Sprint Dates: | 04/04/2022 - 04/17/2022
Part of ID # | Task (to-do) | Description / Notes | Assigned To (Team Member) | Est. Time (Hours) | Total Hours: | 150
10 | Storyline
11 |  | Why are they trying to get the egg? Why will the egg end the war? | TR, KM, IR, AM, JS | 7
12 |  | Where are they? | TR, KM, IR, AM, JS | 7
13 |  | Who are they? | TR, KM, IR, AM, JS | 7
14 |  | What is the goal? | TR, KM, IR, AM, JS | 7
15 |  | When is this taking place? | TR, KM, IR, AM, JS | 7
16 |  | How will the players get the egg? | TR, KM, IR, AM, JS | 7
1 | Game Layout
2 |  | Determine tile status: normal, combat, trap, and cards | AM, KM | 12
3 |  | Placement of tiles, players, and egg | AM, TR, KM | 12
4 | Gameplay
5 |  | Card Mechanics (3 decks? 15 cards?) | IR | 20
9 |  | Rule Book | TR, KM, IR, AM, JS | 20
6 |  | Board Game Mechanics | JS, IR | 20
7 |  | Player Movement (Dice) | JA, IR | 4
8 |  | Combat | JA, IR | 20
Revisions
Revisions From Play Testing