## Product Backlog
Project Name: World War Egg |  | GAM125 - Sprint Backlog
Team: W-W-E
Degree | Team Member (Full Name) | Team Role / Interests | Sprint Information
Game Art & Animation and Advertising Art | Tiffany Roberts | Leader/Producer | Sprint Number: | 2
Computer Science and Game Design | Kaitlyn Moeller | Designer
Game Art & Animation (BFA) | Isabel Ramos | Artist | Days In Sprint: | 13
Game Programming | Anthony Medina | Designer
Game Design | Jasmyn Svetic | Artist | Sprint Dates: | 04/18/2022 - 04/30/2022
1 = Important 2 = Semi Important 3 = Not as important
Part of ID # | Task (to-do) | Description / Notes | Assigned To (Team Member) | Est. Time (Hours) | Total Hours: | 60.5
| Story - 3 | Put on back of rule sheet | JS | 2.5
| Card Art (Front) - 2 | Concept art | IR, KM | 7
|  | Final art and color | IR, KM | 10
| Card Descriptions & Sizing - 1 | Revise | AM | 1.5
| Board Art - 2 | Art and placement | IR, KM, TR | 1.5
| Board Space Sizes - 1 | Revise | TR | 1
| Board Starting Points - 1 | Concept art | TR | 2
|  | Final art and color | TR | 2
| Player Pieces - 1 | Concept art | IR, KM | 4
|  | Final art, coloring, and sizing | IR, KM | 8
| Rules - 2 | Revise | AM, TR, JS | 1.5
| Egg Piece - 2 | Concept Art | TR | 2
|  | Final art, coloring, and sizing | TR | 5
| Player Abilities - 1 | Identify and revise | AM | 1.5
| How to Defeat the Boss - 2 | Detail how players can defeat the boss | AM | 1
| How to Win the Egg - 2 | Detail how players can obtain the egg | AM | 1
| Boss Art - 1 | Concept art | TR | 2.5
|  | Final art and color | TR | 2
| Player Cards - 2 | Art (back) Symbol | TR, JS | 1.5
|  | Abilities (Front Placement) | AM | 1
|  | Character art (Front Placement) | AM | 1
|  | Character name (general, knight, archer, & healer) (Front Placement) | AM | 1